## 10.10.2022
Yassine - Project owner
| Responsible | Action
1. To reconfirm the range, sizes and specifications are available by Nour- mainly related to JIS. Range of MONBAT for Bin Shihon. | Yassine | to reduce 4 variations D31 and to focus on 2 specs. L4 is not available.
2. Bahrain order for High Heat (we have max 60 days or order will be canceled and custoemr lost) | Tatyana / Mario/ Yassine | Qty given to Wassim, ETA 2-3 weeks for PE, Paper, Magic eye , dispatch 11,10,2022? Akumsan lids- 5 weeks to arrive ? Resin - ?
Fast Track delivery !!!
3. Adopting of Nour Premium label for Bin Shihon | Yassine/ Zlatina | to develop labels(2-3 days )
4. Adopting of Nour carton box for Bin Shihon | Yassine/ Zlatina | to develop carton box (2-3 days )
5. Date of production on the battery MM/YY | Ramzi/Mariyan | Confirmed,
6. Certification body to be appointed | Yassine | to check CB available in Tunis and approved for SASO certification (TUV, Intertek, BV)
7. Factory Audit for SASO IEC 60095:2018 | Yassine | to check CB available in Tunis and approved for SASO certification (TUV, Intertek, BV)
8. ISO testing lab for protocols. Time frame. | Mariyan | To look and decide where to test batteries.
9. Supply Chain of materials | Tatyana/ Wassim | already started.
10. Certificate of Origin / Technical Date Sheet | Yassine | to follow up with Authorities
11. Base Price List, business terms, conditions, Incoterms | Yassine / Vili | to transfer full package of info 10-11.10.2022
1900$ From BG to Jeddah port or for Damman port.

## 13.10.2022
Yassine - Project owner
| Responsible | Status 13.10.2022
1. To reconfirm the range, sizes and specifications are available by Nour- mainly related to JIS. Range of MONBAT for Bin Shihon. | Yassine/ Vili | Revised range is proposed to BH, waiting approval by 15.10.2022.
2. Bahrain order for High Heat (we have max 60 days or order will be canceled and custoemr lost) | Tatyana / Wassim/ Yassine | week 42 - dispatch of raw materials for Bahrain + partially for BH
to give full SKU specification (MONBAT AND NOUR SKUs)
Wassim to place order ASAP!
3. Adopting of Nour Premium label for Bin Shihon | Yassine/ Zlatina/ Vili | New design is done, waits approval by Bin Shihon
4. Adopting of Nour carton box for Bin Shihon | Yassine/ Zlatina/ Vili | New design is done, waits approval by Bin Shihon
5. Date of production on the battery MM/YY | Ramzi/Mariyan | Confirmed,
6. Certification body to be appointed | Yassine/Mariyan/Ashraf | Only Intertek Tunisia is able to offer SASO; Which Intertek Office is in charge for Tunis?
| Vili | to provide check list with necessary documents
7. Factory Audit for SASO IEC 60095:2018 | Yassine/Mariyan/Ashraf | Intertek
8. Accredited ISO 17025 testing lab for protocols. Battery Standard IEC 60095-2018. | Mariyan | 1) Two labs are contacted, Germany and Dubai. Waiting feedback.
2) One Lab in Tunis
3) Possibe MGLAB?
9. Certificate of Origin / Technical Date Sheet | Yassine | Process Started, week 44 October to be completed
10. Base Price List, business terms, conditions, Incoterms | Yassine / Vili | Commercial terms are transferred to Yassine
BUT customer expects additional 7% discount (same as from BG)
1900$ From BG to Jeddah port or for Damman port.
1900$ From TN to Jeddah port (CFR)
1900$ From TN to Dammam port (CFR)

## 20.10.2022
Yassine - Project owner
| Responsible |  | Status 20.10.2022
1. To reconfirm the range, sizes and specifications are available by Nour- mainly related to JIS. Range of MONBAT for Bin Shihon. | Yassine/ Vili | Range is approved and Finalized. | Done
2. Bahrain order for High Heat (we have max 60 days or order will be canceled and custoemr lost) | Tatyana / Wassim/ Yassine | week 42 - dispatch of raw materials for Bahrain + partially for BH | Done
|  | to give full SKU specification (MONBAT AND NOUR SKUs) | Done
|  | Wassim to place order ASAP! | Pending
3. Adopting of Nour Premium label for Bin Shihon | Yassine/ Zlatina/ Vili | New Logo of Bin Shihon was replaced, waiting approval by BH | Pending
4. Adopting of Nour carton box for Bin Shihon | Yassine/ Zlatina/ Vili | New Logo of Bin Shihon was replaced, waiting approval by BH | Pending
5. Date of production on the battery MM/YY | Ramzi/Mariyan | Available Equipment to fulfil marking on battery | Done
6. Certification body to be appointed | Yassine/Mariyan/Ashraf | Only Intertek Tunisia is able to offer SASO; Which Intertek Office is in charge for Tunis? | Pending
| Vili | to provide check list with necessary documents | Done
7. Factory Audit for SASO IEC 60095:2018 | Yassine/Mariyan/Ashraf | Intertek | Pending
8. Appointing ISO 17025 for testing. Battery Standard IEC 60095-2018. | Mariyan/ Achraf / Stanislav | 1) Two labs are contacted, Germany and Dubai. Waiting feedback. | Done, rejected option
|  | 2) One Lab in Tunis | Done, rejected option
|  | 3) Possibe MGLAB? | Done, MG LAB appointed
9. Certificate of Origin / Technical Date Sheet | Yassine / Stanislav, Imen | Process Started, week 44 October to be completed | Pending
10. Base Price List, business terms, conditions, Incoterms | Yassine / Vili | Commercial terms are transferred to Yassine | Done
|  | customer expects additional 7% discount (same as from BG). NC Analysis to be done | pending
11. Sew Freight Cost | Yassine/ Wassim | 1900$ From BG to Jeddah port or for Damman port. | Done
|  | 1900$ From TN to Jeddah port (CFR) | Done
|  | 2600$ From TN to Dammam port (CFR) | Done

## Sheet2
free time 15 days